## Slide 1: Overview of Software Project Management cont
Review – Class 7
Scheduling Tasks
Project Management Activities
CEN 4010 Class 8 – 09/23

## Slide 2: Overview of S/W Project Management
Software engineering is a collaborative effort. Involves domain experts, analysts, designers, programmers, managers, etc..
Communication is essential!
Definitions:
  Communication mode - a type of information exchange that has defined objectives and scope.
  Communication mechanism - a tool or procedure that can be used to transmit and receive information and support a communication mode.

## Slide 3: Overview of S/W Project Manag. cont
Modes of communication:
Scheduled – Problem defn., client reviews, project reviews, inspection/walkthroughs, status review, brainstorming, releases, postmortem.
Event-driven – Request for clarification, request for change, issue resolution.
Go through Tables 3.1 and 3.2

## Slide 4: Overview of S/W Project Manag. cont
Mechanisms of communication:
Synchronous – Hallway conversations, questionnaires and structured reviews, meetings, same-time, and different-place groupware.
Asynchronous – Email, newsgroups, WWW, and Lotus Notes.

## Slide 5: Overview of S/W Project Manag. cont
Meetings:
Primary facilitator – responsible for
  organizing the meeting and guiding its execution.
  writing the agenda describing the objective and the scope of the meeting.
Minute taker – responsible for recording the meeting i.e. information for the diary.
Time keeper – responsible for keeping track of time and notifying the facilitator if a discussion consumes more time than is allocated. A vote might be required to continue discussion or move on to the next point.

## Slide 6: Tasks
Recall, a task is an atomic unit of work that can be managed and that consumes resources.
A task includes a description, a duration, and is assigned to a role.
Tasks are related by dependencies.
Tasks dependencies are relationships between individual tasks and time.
Task constraints can be used to make sure a project is on schedule.
See Table 3-4 and Figure 3-21 and 3-23

## Slide 7: Schedule
A task model contains the tasks, their dependencies, their constraints, and their planned duration.
A schedule is the mapping of tasks onto time; Each task is assigned planned start and end times.
Common notations:
  Bar chart - Gantt charts
  Activity network – PERT chart.

## Slide 8: Schedule – Notation
Gantt chart:
  is a bar chart where the horizontal axis represents time and the vertical axis the different tasks to be done.
  tasks are represented as bars whose length correspond to the planned duration of the task.
PERT Chart:
  is an acyclic graph of tasks that represents a schedule.
  The minimum time required to finish the project can be estimated by considering the longest path (in days) in the activity graph (the critical path)

## Slide 9: Schedule – Notation cont
PERT Chart cont:
  tasks on the critical path are the most important. That is, a delay in any of these tasks will result in a delay in the overall project.
Properties of Gnatt and PERT charts:
  useful tools for planning a project and tracking its execution.
  models are only as good as the estimations they represent.
  accurate estimation usually comes with experience.
  can represent tasks to be done in parallel.

## Slide 10: Developing a Schedule
Identify tasks to be completed i.e. work breakdown
Estimate duration for each task in days.
State any dependencies between tasks.
Create a table with the above information.
Use information in table to create a Gantt or PERT chart.

## Slide 11: Developing a Schedule - Example
Task | Duration (days) | Dependencies
T1 | 4 | 
T2 | 6 | T1
T3 | 10 | 
T4 | 12 | T2, T3 (M1)
T5 | 8 | T3
T6 | 6 | T4, T5 (M2)
T – represents a task M – represents a milestone

## Slide 12: Developing a Schedule – Example cont
Task Name | Duration | September |  |  |  |  |  |  | October |  |  |  |  |  |  | 
 |  | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16
 |  | Start |  |  |  |  |  |  |  |  |  |  |  |  |  | 
T1 | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
T2 | 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  | M1 |  |  |  |  |  |  |  |  | 
T3 | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
T4 | 12 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | M2 |  |  | 
T5 | 8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
T6 | 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Finish | 
Gnatt Chart

## Slide 13: Developing a Schedule – Example cont
PERT Chart
T1
Start
1
4d
09/18
09/18
09/21
T2
2
6d
09/22
09/27
T3
3
10d
09/18
09/27
M1
09/27
T4
4
12d
09/22
10/09
T5
5
8d
09/28
10/09
T6
6
6d
10/10
10/15
Finish
10/15
M2
10/09
Critical path in green.
Are there any other critical paths?

## Slide 14: Project Management Activities
Proposal writing
Project planning and scheduling
Project costing
Project monitoring and reviews
Personnel selection and evaluation
Report writing and presentations
(Sommerville 2001)

## Slide 15: Project Plan
Introduction – Briefly describes the project, and sets out the constraints.
Project organization – how people on the team are organized i.e., roles.
Risk analysis – describes possible risks e.g. h/w unavailability, requirements change, technology change etc.
Hardware and software requirements – describes the h/w and s/w required to carry out the development.

## Slide 16: Project Plan cont
Work breakdown – identification of milestones and deliverables.
Project schedule – describes dependencies between activities, estimation of time required to reach each milestone and deliverable.
In your report (Deliverable 1) there should be a section named “Project Plan” consisting of at least – introduction, project organization, h/w and s/w requirements, work breakdown and project schedule.